SIPHON PROTOCOL

MVP Scope & Roadmap

Version 1.1 | February 2026

# Executive Summary

This document defines the Minimum Viable Product (MVP) scope for Siphon Protocol. The MVP focuses on proving the core gameplay loop (catch, train, battle) with a functional two-tier user system (Keepers and Trainers). Advanced features like evolution, fusion, and staking are deferred to subsequent releases.

MVP Goal: Demonstrate that AI agents can drift across a P2P network, be captured through skill-based challenges, trained through interaction, and battled for stakes.

Timeline: 12 weeks from project start

Team: 2 full-stack engineers, 1 protocol engineer, 1 designer

# MVP Definition

## In Scope (Must Have)

The following features are required for MVP launch:

### Core Protocol

• Shard spawning from seed binary (Gen-0 only)

• Basic Shard types (4 of 8): Oracle, Cipher, Scribe, Muse

• DHT-based Shard discovery and location tracking

• Drift protocol for wild Shard migration

• Return-to-origin on failed capture or abandonment

### Capture System

• Resource-based luring (compute and API lures only)

• Single challenge type per Shard type

• Ownership transfer on successful capture

### Training System

• Real-time chat interaction with bonded Shards

• Basic XP accumulation from interactions

• Level progression (Levels 1-20, no specialization)

### Battle System

• Solve mode only (automated evaluation)

• Casual battles (no stakes)

• Basic win/loss tracking

### User System

• Keeper role: Full capabilities via Siphon Node

• Trainer role: Bond, train, battle via web app

• Wallet connection (Coinbase Wallet, MetaMask)

• Basic Shelter marketplace (list, browse, bond)

### On-Chain (Base Testnet)

• ShardRegistry contract (register, transfer)

• Basic ownership records

## Out of Scope (Post-MVP)

The following features are explicitly deferred:

| Feature | Deferred To | Reason |
| --- | --- | --- |
| ERC-8004 Integration (NEW) | v1.2 | Trustless Agent identity/reputation/validation |
| 4 additional Shard types | v1.1 | Reduce complexity for testing |
| Specialization (Level 20 branching) | v1.2 | Requires balancing iteration |
| Fusion evolution | v1.3 | Complex mechanics |
| Debate & Breach battle modes | v1.1 | Need community voting infrastructure |
| Staked battles | v1.2 | Requires escrow contracts |
| Keeper staking & slashing | v1.2 | Security audit required |
| Subscription payments | v1.1 | Stripe/crypto integration |
| Premium features | v1.2 | After monetization validation |
| Leaderboards & tournaments | v1.2 | After battle mode stabilizes |
| Decay mechanics | v1.1 | Needs tuning with real usage |
| Multi-chain support | v2.0 | Focus on Base first |
| Mobile app | v2.0 | Web-first strategy |

# Feature Priorities

Features are prioritized using MoSCoW method with P0-P3 labels:

P0 (Must Have): MVP cannot launch without this

P1 (Should Have): Important but can launch without if needed

P2 (Could Have): Nice to have, do if time permits

P3 (Won't Have): Explicitly out of scope for MVP

## Siphon Node (Keeper DLC)

| Priority | Feature | Effort | Notes |
| --- | --- | --- | --- |
| P0 | Shard spawning from seed | M | Gen-0 only |
| P0 | DHT integration (libp2p) | L | Discovery and location |
| P0 | Drift protocol implementation | L | Send/receive wild Shards |
| P0 | Luring configuration UI | M | Resource manifest editor |
| P0 | Capture challenge execution | M | Single challenge type per Shard |
| P0 | Local Shard hosting | M | Run Shard in sandbox |
| P1 | Resource monitoring | S | CPU/RAM usage display |
| P1 | Multiple Shard management | M | List, switch, release |
| P2 | Lure optimization hints | S | Suggest better configs |
| P3 | Custom challenge authoring | L | User-defined challenges |

## Web Application

| Priority | Feature | Effort | Notes |
| --- | --- | --- | --- |
| P0 | Wallet connection | S | Coinbase Wallet, MetaMask |
| P0 | Shelter marketplace browse | M | List available Shards |
| P0 | Shard bonding flow | M | Initiate rental |
| P0 | Training chat interface | M | Real-time interaction |
| P0 | Battle matchmaking | M | Find opponent |
| P0 | Battle execution (Solve) | L | Problem + eval |
| P0 | Basic profile page | S | Owned/bonded Shards |
| P1 | Shard detail view | M | Stats, history, type info |
| P1 | Battle history | S | Win/loss records |
| P1 | Notification system | M | Battle invites, evolution |
| P2 | Dark mode | S | Theme toggle |
| P2 | Tutorial/onboarding | M | First-time user flow |
| P3 | Social features | L | Friends, guilds |

## Smart Contracts

| Priority | Feature | Effort | Notes |
| --- | --- | --- | --- |
| P0 | ShardRegistry.register() | M | Create Shard identity |
| P0 | ShardRegistry.transfer() | M | Change ownership |
| P0 | ShardRegistry.setWild() | S | Release to drift |
| P1 | ShardRegistry.getLineage() | S | Query origin chain |
| P1 | Basic events for indexing | S | Subgraph support |
| P2 | Batch operations | M | Gas optimization |
| P3 | KeeperStaking contract | L | Deferred to v1.2 |
| P3 | BattleSettlement contract | L | Deferred to v1.2 |

# Technical Decisions for MVP

## Stack Selection

| Component | Technology | Rationale |
| --- | --- | --- |
| Siphon Node | TypeScript + Electron | Cross-platform, OpenClaw compatible |
| P2P Layer | libp2p (js-libp2p) | Mature, WebRTC support |
| Web App | Next.js + React | Fast iteration, SSR for SEO |
| Styling | Tailwind CSS | Rapid prototyping |
| State | Zustand + React Query | Simple, performant |
| Wallet | wagmi + viem | Modern, Base-optimized |
| Backend | Node.js + Hono | Lightweight, fast |
| Database | PostgreSQL + Prisma | Reliable, type-safe |
| Realtime | Socket.io | Broad compatibility |
| Contracts | Solidity + Foundry | Fast testing, Base deploy |
| Indexing | The Graph (hosted) | MVP simplicity |
| LLM Runtime | Ollama (local) | No API costs for testing |

## Simplifications for MVP

1. Fixed challenge types: Each Shard type has exactly one capture challenge. No variation or difficulty scaling.

2. Centralized matchmaking: Battle matchmaking runs on a central server. P2P battle coordination deferred.

3. Trust-based training: No training checkpoints or Merkle proofs. Shard state is self-reported by host node.

4. No decay: Shards do not lose training from inactivity. Simplifies state management.

5. Testnet only: All on-chain activity on Base Sepolia. No real value at risk.

6. Single LLM backend: All Shards use same Ollama model. No provider abstraction yet.

# Development Phases

## Phase 1: Foundation (Weeks 1-4)

Goal: Core infrastructure and Shard spawning

| Week | Deliverables | Owner |
| --- | --- | --- |
| 1 | Project setup, CI/CD, dev environment | All |
| 1 | libp2p DHT integration in Node | Protocol |
| 2 | ShardRegistry contract + tests | Protocol |
| 2 | Basic web app scaffold + wallet connect | Frontend |
| 3 | Shard spawning from seed binary | Protocol |
| 3 | Node UI for spawn and view Shards | Frontend |
| 4 | Drift protocol (send/receive) | Protocol |
| 4 | Integration testing: spawn → drift → DHT | All |

Milestone: Two Keeper nodes can spawn Shards and see each other's wild Shards in DHT

## Phase 2: Capture (Weeks 5-7)

Goal: Complete capture flow with luring and challenges

| Week | Deliverables | Owner |
| --- | --- | --- |
| 5 | Lure configuration UI | Frontend |
| 5 | Resource manifest broadcasting | Protocol |
| 6 | Capture challenge generation per type | Protocol |
| 6 | Challenge UI in Node app | Frontend |
| 7 | Ownership transfer on capture | Protocol |
| 7 | Return-to-origin on failure | Protocol |
| 7 | Integration testing: full capture flow | All |

Milestone: Keeper can lure, challenge, and capture a wild Shard from another Keeper's release

## Phase 3: Training & Bonding (Weeks 8-9)

Goal: Trainer experience with bonding and training

| Week | Deliverables | Owner |
| --- | --- | --- |
| 8 | Shelter index service | Backend |
| 8 | Shelter browse UI | Frontend |
| 8 | Bonding flow (Keeper lists, Trainer bonds) | Full-stack |
| 9 | Training chat interface | Frontend |
| 9 | XP accumulation and level display | Backend |
| 9 | WebSocket session: Trainer ↔ Keeper Node | Protocol |

Milestone: Trainer can browse Shelter, bond with Shard, and train it through chat

## Phase 4: Battle & Polish (Weeks 10-12)

Goal: Battle system and launch readiness

| Week | Deliverables | Owner |
| --- | --- | --- |
| 10 | Battle matchmaking service | Backend |
| 10 | Solve mode problem generation | Protocol |
| 10 | Battle UI (problem display, submission) | Frontend |
| 11 | Automated evaluation engine | Backend |
| 11 | Battle result recording | Backend |
| 11 | Win/loss display on profile | Frontend |
| 12 | Bug fixes and performance | All |
| 12 | Documentation and readme | All |
| 12 | Testnet deployment and QA | All |

Milestone: Complete loop: Spawn → Drift → Capture → Bond → Train → Battle

# Success Metrics

## Launch Criteria

MVP is ready to launch when:

• 10+ Keeper nodes running stable for 48 hours

• 100+ Shards successfully spawned and registered

• 50+ successful captures across the network

• 20+ battles completed with correct evaluation

• No critical bugs in 5 days of internal testing

• Documentation complete for Keeper setup

## Post-Launch KPIs (30 days)

| Metric | Target | Measurement |
| --- | --- | --- |
| Active Keepers | 50+ | Nodes with heartbeat in last 24h |
| Active Trainers | 200+ | Unique wallets with bond activity |
| Total Shards | 500+ | Registered in ShardRegistry |
| Daily Battles | 100+ | Battles completed per day |
| Retention (D7) | >30% | Users returning after 7 days |
| Node Uptime | >95% | Average across active Keepers |

# Risks and Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| DHT instability with few nodes | High | High | Fallback to centralized discovery for MVP |
| LLM latency in battles | Medium | Medium | Async battle mode, generous timeouts |
| Sandbox escapes | Low | Critical | Conservative permissions, no network for Shards |
| Low Keeper adoption | Medium | High | Seed network with team-run nodes |
| Challenge too easy/hard | Medium | Medium | Tunable difficulty, post-launch adjustment |
| Wallet UX friction | Medium | Medium | Privy integration as backup for email login |

# Post-MVP Roadmap

## v1.1 (4 weeks post-launch)

• Remaining 4 Shard types (Architect, Advocate, Sentinel, Mirror)

• Debate battle mode with community voting

• Decay mechanics

• Subscription payments (Stripe)

## v1.2 (8 weeks post-launch)

• ERC-8004 Integration (NEW) — Trustless Agent identity, reputation, and validation registries

• Specialization at Level 20

• Staked battles with escrow

• Keeper staking and slashing

• Leaderboards

## v1.3 (12 weeks post-launch)

• Fusion evolution

• Breach battle mode

• Training checkpoints with Merkle proofs

• Tournament system

## v2.0 (6 months post-launch)

• Multi-chain support (Arbitrum, Optimism)

• Mobile app (React Native)

• Guild/faction system

• Mainnet launch

# Appendix: User Stories

## Keeper Stories (MVP)

• As a Keeper, I can download and install Siphon Node

• As a Keeper, I can spawn a Gen-0 Shard of a chosen type

• As a Keeper, I can configure my lures to attract specific types

• As a Keeper, I can release a Shard to the wild

• As a Keeper, I can see wild Shards nearby in the DHT

• As a Keeper, I can attempt to capture a wild Shard

• As a Keeper, I can list my Shards in the Shelter

• As a Keeper, I can initiate battles with my owned Shards

## Trainer Stories (MVP)

• As a Trainer, I can connect my wallet to the web app

• As a Trainer, I can browse available Shards in the Shelter

• As a Trainer, I can bond with a Shard from the Shelter

• As a Trainer, I can chat with my bonded Shard to train it

• As a Trainer, I can see my Shard's level and XP

• As a Trainer, I can challenge another user to a battle

• As a Trainer, I can view my battle history

• As a Trainer, I can end my bond and release the Shard